## Sheet1
Risk ID | Risk Name | Consequence (X Axis) | Likelihood (Y Axis) | Risk Management Heat Map Tool
1 | Incorrect database design | 3 | 3
2 | Incorrect code in ordering module | 2 | 4
3 | Inaccurate, sloppy design of the website | 4 | 2
4 | Lack of appropriate tools to support clients in timely fashion | 2 | 5
5 | Inappropriate funding of the implementation process | 5 | 2
6 | Additional expenditures for implementation | 1 | 4
7 | Delays during implementation | 1 | 5
8 | Training caused delays | 4 | 4
9 | Technical issues (substantial website downtimes) | 5 | 1
10 | Additional expenditures for training needs | 1 | 1
[5 empty] | Risk ID | Risk Description | Risk Disposition
[5 empty] | 1 | Incorrect database design | Avoid
[5 empty] | 2 | Incorrect code in ordering module | Avoid
[5 empty] | 3 | Inaccurate, sloppy design of the website | Mitigate
[5 empty] | 4 | Lack of appropriate tools to support clients in timely fashion | Transfer
[5 empty] | 5 | Inappropriate funding of the implementation process | Mitigate
[5 empty] | 6 | Additional expenditures for implementation | Mitigate
[5 empty] | 7 | Delays during implementation | Accept
[5 empty] | 8 | Training caused delays | Accept
[5 empty] | 9 | Technical issues (substantial website downtimes) | Avoid
[5 empty] | 10 | Additional expenditures for training needs | Accept
Notes: 1. Just enter the 'Consequence' (derived from the Composite Impact) and 'Likelihood (Probability of Occurrence) scores into a row and the item will automatically populate in the proper spot on the chart. 2. Data values for both axes must be >= 0 and <= 5. 3. If the data changes, the marker moves as well. 4. Risk ID numbers can also be changed and the chart will update. 5. In the event two or more circles are too close, the number can be dragged out of a circle wherever needed. 6. The chart pastes well into PowerPoint (even live link if desired). 7. Once you've added data, save the file with different name and location.